## Sheet1
PROJECT SUMMARY COSTS | Total
Labor Total (Approximate) | 7782.55
Furniture and Equipment | 74725
Project Total (Approximate) | 82507.55
LABOUR COSTS | HOURLY RATE($)
Shruti Rao | 65
Isabella Smith | 55
Art Peters | 50
Bob DeSantis | 42.5
Nick Thomas | 43.75
Caroline Jansen | 45
AVERAGE | 50.2083
Labor Costs
Fibre Light Network Upgrade | Time(Hrs) | Hourly Rate | Approx. Cost
Initiate Project
Identify Stakeholders | 14 | 50.21 | 702.94
Plan Project
Determining Deliverables | 14 | 50.21 | 702.94
Evaluating Risks | 10 | 50.21 | 502.1
Finalising the staffing and structure and responsibilities | 10 | 50.21 | 502.1
Present The Executive Overview | 8 | 50.21 | 401.68
Make necessary changes | 10 | 50.21 | 502.1
Charter Approval | 10 | 50.21 | 502.1
Execute Project
Order Furniture | 0 | 50.21 | 0
Order Cables/ WAP's | 14 | 50.21 | 702.94
Order Workstations | 2 | 50.21 | 100.42
Setup
Installation of furniture | 12 | 50.21 | 602.52
Intallation of other equipments | 11 | 50.21 | 552.31
Payment
Payment made to the furniture contractor | 12 | 50.21 | 602.52
Payment made for other equipments | 12 | 50.21 | 602.52
Close Project
Check that all furniture and equipments have been installed correctly | 16 | 50.21 | 803.36
Labor Total (Approximate) | 155 | 50.21 | 7782.55
Labor Total (High) |  | 42.5 | 6587.5
Labor Total (Low) |  | 65 | 10075
Equipment and Furniture Costs
Name | Number | Cost(Each) | Total
Laptops with software suite | 12 | 2125 | 25500
VoIP Handsets | 12 | 545 | 6540
Cubicle Furniture | 12 | 2600 | 31200
Kyocera High-speed Copier/Printer | 1 | 5075 | 5075
Cisco Aironet Wireless Access Points | 4 | 620 | 2480
Ciena 3926 Aggregation Switch | 1 | 3450 | 3450
Cat 6E Network Cabling | 1 | 480 | 480
Equipment and Furniture Costs Total |  |  | 74725